## Sheet1
1. Requirements Definition (Phase 1)
1.01 | Requirements funding
1.01.01 | Review project request
1.01.02 | Establish preliminary justification
1.01.03 | Fund Phase 1
1.01.04 | Prioritize project
1.01.05 | Establish project team
1.02 | Define problem or opportunity
1.02.01 | Interview users
1.02.02 | Examine operation and reports
1.02.03 | Document problem from symptoms
1.02.04 | Define project scope
1.03 | Analyze existing system
1.03.01 | Assemble documentation on existing system
1.03.02 | Identify data flows
1.03.03 | Identify external interfaces
1.03.04 | Identify problem domain
1.04 | Document system requirements
1.04.01 | Document output information requirements
1.04.02 | Document interface constraints
1.04.03 | Document audit trail constraints
1.04.04 | Document turnaround or response time
1.04.05 | Document security constraints
1.04.06 | Document physical environment constraints or requirements
1.05 | Validate against systems architecture
1.05.01 | Compare requirements with systems architecture
1.05.02 | Identify possible inconsistencies
1.05.03 | Identify conflicting and concurrent development
1.05.04 | Identify recommended changes to systems architecture
1.05.05 | Identify recommended changes to strategic implementation plan
1.06 | Management review / Phase 2 funding
1.06.01 | Plan next phase
1.06.02 | Reevaluate development costs
1.06.03 | Reevaluate justification
1.06.04 | Obtain user requirements consensus
1.06.05 | Obtain technical consensus
2 | Logical Design (Phase 2)
2.01 | Identify detailed data requirements
2.01.01 | Identify output requirements
2.01.02 | Decompose output data
2.01.03 | Identify input requirements
2.01.04 | Identify sources of input
2.02 | Develop prototype or user system view
2.02.01 | Design interactive screens
2.02.02 | Design reports
2.03 | Design database
2.03.01 | Define logical data relations
2.03.02 | Design data structure
2.03.03 | Validate database design
2.04 | Structure processes
2.04.01 | Isolate highly related data
2.04.02 | Reconstruct processes to correspond with output requirements
2.04.03 | Identify reusable process structures
2.05 | Design Interfaces
2.05.01 | Design external data interfaces
2.05.02 | Design human interfaces
2.05.03 | Design intersystem interfaces
2.06 | Specify all inputs and outputs
2.06.01 | Define data and interface relations
2.06.02 | Define data and system relations
2.07 | Develop preliminary test and conversion procedures
2.07.01 | Identify test requirements
2.07.02 | Create test checklist
2.07.03 | Identify conversion requirements
2.07.04 | Create conversion checklist
2.08 | Validate logical design
2.08.01 | Validate data relations
2.08.02 | Validate process relations
2.08.03 | Validate process logic
2.08.04 | Trace requirements to design
2.09 | Validate against system architecture
2.09.01 | Compare logical design with systems architecture
2.09.02 | Identify possible inconsistencies
2.09.03 | Identify conflicting and concurrent development
2.09.04 | Identify recommended changes to systems architecture
2.09.05 | Identify recommended changes to strategic implementation plan
2.1 | Management review / Phase 3 funding
2.10.01 | Plan next phase
2.10.02 | Reevaluate development costs
2.10.03 | Reevaluate justification
2.10.04 | Obtain user requirements consensus
2.10.05 | Obtain technical consensus
3 | Physical Design (Phase 3)
3.01 | Design or specify physical database
3.01.01 | Review logical database design
3.01.02 | Determine access methods to be used
3.01.03 | Normalize database
3.01.04 | Design database architecture
3.01.05 | Identify reusable database structures
3.01.06 | Develop detailed database layout
3.01.07 | Develop database file, record, and schema descriptions
3.01.08 | Develop module calling sequences
3.01.09 | Update data dictionary entries
3.01.10 | Validate physical database design
3.02 | Design processing structure
3.02.01 | Compose process structures from data decomposition
3.02.02 | Identify physical subsystems
3.02.03 | Identify physical programs
3.02.04 | Identify reusable programs
3.02.05 | Eliminate process redundancies
3.02.06 | Develop teleprocessing network specifications
3.03 | Design processing logic
3.03.01 | Design calling sequences
3.03.02 | Develop calculation specifications
3.03.03 | Design interface logic
3.03.04 | Design security logic
3.03.05 | Design error recovery logic
3.04 | Define procedures
3.04.01 | Review logical system design user interfaces
3.04.02 | Develop interactive data-entry procedures
3.04.03 | Develop screen specifications
3.04.04 | Design input forms
3.04.05 | Develop physical report specifications
3.04.06 | Develop user operating procedures
3.04.07 | Develop data processing operations run procedures
3.05 | Refine test/conversion procedures
3.05.01 | Review test/conversion plans
3.05.02 | Update test/conversion plans
3.06 | Validate physical design
3.06.01 | Validate data relations
3.06.02 | Validate process relations
3.06.03 | Validate process logic
3.06.04 | Validate procedures
3.06.05 | Validate teleprocessing network specifications
3.06.06 | Validate system timing and sizing requirements
3.07 | Validate against systems architecture
3.07.01 | Compare physical design with systems architecture
3.07.02 | Identify possible inconsistencies
3.07.03 | Identify conflicting / concurrent development
3.07.04 | Identify recommended changes to systems architecture
3.08 | Management review / Phase 3 funding
3.08.01 | Plan next phase
3.08.02 | Reevaluate development costs
3.08.03 | Reevaluate justification
3.08.04 | Obtain user requirements consensus
3.08.05 | Obtain technical consensus
4 | Programming and Unit Testing (Phase 4)
4.01 | Decompose program modules
4.01.01 | Identify program modules
4.01.02 | Identify program module input and output
4.01.03 | Identify reusable modules
4.01.04 | Eliminate module redundancies
4.02 | Develop program modules
4.02.01 | Develop detailed module logic
4.02.02 | Validate module logic
4.02.03 | Code module
4.02.04 | Develop module test data
4.02.05 | Develop call and called stubs
4.02.06 | Unit test program
4.03 | Update test/conversion procedures
4.03.01 | Review test/conversion plans
4.03.02 | Update test/conversion plans
4.04 | Management review / Phase 3 funding
4.04.01 | Plan next phase
4.04.02 | Reevaluate development costs
4.04.03 | Reevaluate justification
4.04.04 | Obtain user requirements consensus
4.04.05 | Obtain technical consensus
5 | System Testing (Phase 5)
5.01 | Finalize integrated system test plan
5.01.01 | Review interim test procedures
5.01.02 | Develop integration test procedures
5.01.03 | Develop integration test plan
5.01.04 | Assign integration test responsibilities
5.01.05 | Develop integration test data
5.01.06 | Train data processing personnel
5.02 | Finalize user acceptance/training test plan
5.02.01 | Review interim test procedures
5.02.02 | Develop user acceptance criteria
5.02.03 | Develop final user acceptance test procedures
5.02.04 | Develop user acceptance test plan
5.02.05 | Assign user acceptance test responsibilities
5.02.06 | Develop user acceptance test data
5.02.07 | Train users
5.03 | Conduct integration test
5.03.01 | Link programs and copy to test libraries
5.03.02 | Establish test files
5.03.03 | Execute integration test
5.04 | Conduct user acceptance/training test
5.04.01 | Establish user acceptance test files
5.04.02 | Establish test files
5.04.03 | Execute user acceptance test
5.05 | Management review / Phase 3 funding
5.05.01 | Plan next phase
5.05.02 | Reevaluate development costs
5.05.03 | Reevaluate justification
5.05.04 | Obtain user requirements consensus
5.05.05 | Obtain technical consensus
6 | Installation (Phase 6)
6.01 | Finalize conversion plan
6.01.01 | Review interim conversion procedures
6.01.02 | Develop conversion procedures
6.01.03 | Develop conversion plan
6.01.04 | Assign conversion responsibilities
6.02 | Convert files/database
6.03 | Install software
6.04 | Run systems in parallel
6.05 | Turn off old system
6.06 | Management review
6.06.01 | Obtain user requirements consensus
6.06.02 | Obtain technical consensus
6.06.03 | Document recommended changes to architecture
6.06.04 | Document recommended enhancements to system