## Sheet1
Project Title | Parent ID | Status | Task Description | Start Date | End Date | Resource ID
Project Demo | 1.0 | In Progress | Requirements Definition (Phase 1) | 2020-01-01 | 2020-01-31 | Martie Feldtmann
Project Demo | 1.01 | In Progress | Requirements funding | 2020-01-01 | 2020-01-10 | Martie Feldtmann
Project Demo | 1.011 | Completed | Review project request | 2020-01-03 | 2020-01-03 | James DeCola
Project Demo | 1.012 | Deferred | Establish preliminary justification | 2020-01-01 | 2020-01-10 | Jack Stromberg
Project Demo | 1.013 | In Progress | Fund Phase 1 | 2020-01-04 | 2020-01-10 | Jack Stromberg
Project Demo | 1.014 | Not Started | Prioritize project | 2020-01-08 | 2020-01-10 | Martie Feldtmann
Project Demo | 1.015 | Not Started | Establish project team | 2020-01-02 | 2020-01-10 | Bridgette
Project Demo | 1.02 | Deferred | Define problem or opportunity | 2020-01-01 | 2020-01-20 | Jack Stromberg
Project Demo | 1.021 | Deferred | Interview users | 2020-01-05 | 2020-01-18 | Martie Feldtmann
Project Demo | 1.022 | Completed | Examine operation and reports | 2020-01-05 | 2020-01-15 | James DeCola
Project Demo | 1.023 | Completed | Document problem from symptoms | 2020-01-05 | 2020-01-19 | Martie Feldtmann
Project Demo | 1.024 | Not Started | Define project scope | 2020-01-05 | 2020-01-20 | Bridgette
Project Demo | 1.03 | In Progress | Analyze existing system | 2020-01-05 | 2020-01-20 | Lauren Chavez
Project Demo | 1.031 | In Progress | Assemble documentation on existing system | 2020-01-05 | 2020-01-20 | Lauren Chavez
Project Demo | 1.032 | In Progress | Identify data flows | 2020-01-10 | 2020-01-25 | Martie Feldtmann
Project Demo | 1.033 | Not Started | Identify external interfaces | 2020-01-15 | 2020-01-25 | Martie Feldtmann
Project Demo | 1.034 | Deferred | Identify problem domain | 2020-01-15 | 2020-01-25 | Martie Feldtmann
Project Demo | 1.04 | In Progress | Document system requirements | 2020-01-05 | 2020-01-25 | Bridgette
Project Demo | 1.041 | In Progress | Document output information requirements | 2020-01-05 | 2020-01-10 | Jack Stromberg
Project Demo | 1.042 | Not Started | Document interface constraints | 2020-01-08 | 2020-01-12 | Lauren Chavez
Project Demo | 1.043 | Completed | Document audit trail constraints | 2020-01-12 | 2020-01-12 | James DeCola
Project Demo | 1.044 | Completed | Document turnaround or response time | 2020-01-08 | 2020-01-08 | Jack Stromberg
Project Demo | 1.045 | Deferred | Document security constraints | 2020-01-13 | 2020-01-16 | Bridgette
Project Demo | 1.046 | Completed | Document physical environment constraints or requirements | 2020-01-17 | 2020-01-25 | Martie Feldtmann
Project Demo | 1.05 | In Progress | Validate against systems architecture | 2020-01-15 | 2020-01-28 | Martie Feldtmann
Project Demo | 1.051 | Not Started | Compare requirements with systems architecture | 2020-01-15 | 2020-01-20 | Jack Stromberg
Project Demo | 1.052 | Not Started | Identify possible inconsistencies | 2020-01-15 | 2020-01-20 | Bridgette
Project Demo | 1.053 | In Progress | Identify conflicting and concurrent development | 2020-01-21 | 2020-01-22 | Martie Feldtmann
Project Demo | 1.054 | Not Started | Identify recommended changes to systems architecture | 2020-01-21 | 2020-01-24 | Lauren Chavez
Project Demo | 1.055 | Not Started | Identify recommended changes to strategic implementation plan | 2020-01-24 | 2020-01-28 | Bridgette
Project Demo | 1.06 | In Progress | Management review / Phase 2 funding | 2020-01-25 | 2020-01-31 | Bridgette
Project Demo | 1.061 | In Progress | Plan next phase |  |  | James DeCola
Project Demo | 1.062 | Not Started | Reevaluate development costs |  |  | Jack Stromberg
Project Demo | 1.063 | Completed | Reevaluate justification |  |  | Martie Feldtmann
Project Demo | 1.064 | Completed | Obtain user requirements consensus |  |  | Martie Feldtmann
Project Demo | 1.065 | In Progress | Obtain technical consensus |  |  | Lauren Chavez
Project Demo | 2 | Deferred | Logical Design (Phase 2) |  |  | Lauren Chavez
Project Demo | 2.01 | Deferred | Identify detailed data requirements |  |  | Lauren Chavez
Project Demo | 2.011 | Not Started | Identify output requirements |  |  | Martie Feldtmann
Project Demo | 2.012 | In Progress | Decompose output data |  |  | Martie Feldtmann
Project Demo | 2.013 | Not Started | Identify input requirements |  |  | Martie Feldtmann
Project Demo | 2.014 | Completed | Identify sources of input |  |  | James DeCola
Project Demo | 2.02 | In Progress | Develop prototype or user system view |  |  | Martie Feldtmann
Project Demo | 2.021 | Not Started | Design interactive screens |  |  | Jack Stromberg
Project Demo | 2.022 | In Progress | Design reports |  |  | Martie Feldtmann
Project Demo | 2.03 | Not Started | Design database |  |  | James DeCola
Project Demo | 2.031 | In Progress | Define logical data relations |  |  | James DeCola
Project Demo | 2.032 | Deferred | Design data structure |  |  | Bridgette
Project Demo | 2.033 | In Progress | Validate database design |  |  | Lauren Chavez
Project Demo | 2.04 | Completed | Structure processes |  |  | Martie Feldtmann
Project Demo | 2.041 | In Progress | Isolate highly related data |  |  | James DeCola
Project Demo | 2.042 | Not Started | Reconstruct processes to correspond with output requirements |  |  | Bridgette
Project Demo | 2.043 | In Progress | Identify reusable process structures |  |  | James DeCola
Project Demo | 2.05 | Not Started | Design Interfaces |  |  | Martie Feldtmann
Project Demo | 2.051 | Not Started | Design external data interfaces |  |  | Bridgette
Project Demo | 2.052 | Not Started | Design human interfaces |  |  | Bridgette
Project Demo | 2.053 | Completed | Design intersystem interfaces |  |  | Martie Feldtmann
Project Demo | 2.06 | Deferred | Specify all inputs and outputs |  |  | Lauren Chavez
Project Demo | 2.061 | In Progress | Define data and interface relations |  |  | Martie Feldtmann
Project Demo | 2.062 | Completed | Define data and system relations |  |  | Lauren Chavez
Project Demo | 2.07 | Not Started | Develop preliminary test and conversion procedures |  |  | James DeCola
Project Demo | 2.071 | Not Started | Identify test requirements |  |  | Jack Stromberg
Project Demo | 2.072 | Completed | Create test checklist |  |  | Bridgette
Project Demo | 2.073 | Not Started | Identify conversion requirements |  |  | Lauren Chavez
Project Demo | 2.074 | Completed | Create conversion checklist |  |  | Bridgette
Project Demo | 2.08 | Not Started | Validate logical design |  |  | Bridgette
Project Demo | 2.081 | Deferred | Validate data relations |  |  | Bridgette
Project Demo | 2.082 | Not Started | Validate process relations |  |  | Jack Stromberg
Project Demo | 2.083 | Deferred | Validate process logic |  |  | James DeCola
Project Demo | 2.084 | In Progress | Trace requirements to design |  |  | Lauren Chavez
Project Demo | 2.09 | Completed | Validate against system architecture |  |  | Lauren Chavez
Project Demo | 2.091 | Completed | Compare logical design with systems architecture |  |  | Bridgette
Project Demo | 2.092 | Completed | Identify possible inconsistencies |  |  | Jack Stromberg
Project Demo | 2.093 | Completed | Identify conflicting and concurrent development |  |  | Bridgette
Project Demo | 2.094 | In Progress | Identify recommended changes to systems architecture |  |  | Lauren Chavez
Project Demo | 2.095 | Completed | Identify recommended changes to strategic implementation plan |  |  | Lauren Chavez
Project Demo | 2.1 | Deferred | Management review / Phase 3 funding |  |  | Bridgette
Project Demo | 2.101 | Deferred | Plan next phase |  |  | Jack Stromberg
Project Demo | 2.102 | Completed | Reevaluate development costs |  |  | James DeCola
Project Demo | 2.103 | Completed | Reevaluate justification |  |  | Bridgette
Project Demo | 2.104 | In Progress | Obtain user requirements consensus |  |  | James DeCola
Project Demo | 2.105 | Completed | Obtain technical consensus |  |  | Bridgette
Project Demo | 3 | Not Started | Physical Design (Phase 3) |  |  | Jack Stromberg
Project Demo | 3.01 | Not Started | Design or specify physical database |  |  | Bridgette
Project Demo | 3.011 | Completed | Review logical database design |  |  | Bridgette
Project Demo | 3.012 | In Progress | Determine access methods to be used |  |  | Lauren Chavez
Project Demo | 3.013 | Completed | Normalize database |  |  | Bridgette
Project Demo | 3.014 | Not Started | Design database architecture |  |  | Martie Feldtmann
Project Demo | 3.015 | Not Started | Identify reusable database structures |  |  | James DeCola
Project Demo | 3.016 | Not Started | Develop detailed database layout |  |  | Bridgette
Project Demo | 3.017 | In Progress | Develop database file, record, and schema descriptions |  |  | Lauren Chavez
Project Demo | 3.018 | Not Started | Develop module calling sequences |  |  | Martie Feldtmann
Project Demo | 3.019 | Completed | Update data dictionary entries |  |  | Lauren Chavez
Project Demo | 3.0110 | Deferred | Validate physical database design |  |  | Bridgette
Project Demo | 3.02 | In Progress | Design processing structure |  |  | James DeCola
Project Demo | 3.021 | Deferred | Compose process structures from data decomposition |  |  | Martie Feldtmann
Project Demo | 3.022 | Completed | Identify physical subsystems |  |  | Lauren Chavez
Project Demo | 3.023 | Not Started | Identify physical programs |  |  | Lauren Chavez
Project Demo | 3.024 | Completed | Identify reusable programs |  |  | Jack Stromberg
Project Demo | 3.025 | Deferred | Eliminate process redundancies |  |  | Bridgette
Project Demo | 3.026 | Deferred | Develop teleprocessing network specifications |  |  | Jack Stromberg
Project Demo | 3.03 | Deferred | Design processing logic |  |  | Jack Stromberg
Project Demo | 3.031 | In Progress | Design calling sequences |  |  | Lauren Chavez
Project Demo | 3.032 | Deferred | Develop calculation specifications |  |  | Martie Feldtmann
Project Demo | 3.033 | Not Started | Design interface logic |  |  | Jack Stromberg
Project Demo | 3.034 | In Progress | Design security logic |  |  | Jack Stromberg
Project Demo | 3.035 | Completed | Design error recovery logic |  |  | James DeCola
Project Demo | 3.04 | Not Started | Define procedures |  |  | Martie Feldtmann
Project Demo | 3.041 | Not Started | Review logical system design user interfaces |  |  | Bridgette
Project Demo | 3.042 | Not Started | Develop interactive data-entry procedures |  |  | Bridgette
Project Demo | 3.043 | Not Started | Develop screen specifications |  |  | Bridgette
Project Demo | 3.044 | Completed | Design input forms |  |  | Jack Stromberg
Project Demo | 3.045 | Completed | Develop physical report specifications |  |  | Martie Feldtmann
Project Demo | 3.046 | Not Started | Develop user operating procedures |  |  | Bridgette
Project Demo | 3.047 | Deferred | Develop data processing operations run procedures |  |  | Martie Feldtmann
Project Demo | 3.05 | Completed | Refine test/conversion procedures |  |  | Martie Feldtmann
Project Demo | 3.051 | Completed | Review test/conversion plans |  |  | Jack Stromberg
Project Demo | 3.052 | Not Started | Update test/conversion plans |  |  | Jack Stromberg
Project Demo | 3.06 | Not Started | Validate physical design |  |  | Bridgette
Project Demo | 3.061 | Deferred | Validate data relations |  |  | Lauren Chavez
Project Demo | 3.062 | Deferred | Validate process relations |  |  | Lauren Chavez
Project Demo | 3.063 | Deferred | Validate process logic |  |  | Bridgette
Project Demo | 3.064 | Completed | Validate procedures |  |  | Bridgette
Project Demo | 3.065 | Not Started | Validate teleprocessing network specifications |  |  | Jack Stromberg
Project Demo | 3.066 | Completed | Validate system timing and sizing requirements |  |  | Martie Feldtmann
Project Demo | 3.07 | Not Started | Validate against systems architecture |  |  | Lauren Chavez
Project Demo | 3.071 | Not Started | Compare physical design with systems architecture |  |  | James DeCola
Project Demo | 3.072 | Deferred | Identify possible inconsistencies |  |  | Jack Stromberg
Project Demo | 3.073 | Not Started | Identify conflicting / concurrent development |  |  | Lauren Chavez
Project Demo | 3.074 | In Progress | Identify recommended changes to systems architecture |  |  | James DeCola
Project Demo | 3.08 | Completed | Management review / Phase 3 funding |  |  | Jack Stromberg
Project Demo | 3.081 | In Progress | Plan next phase |  |  | Lauren Chavez
Project Demo | 3.082 | Deferred | Reevaluate development costs |  |  | Jack Stromberg
Project Demo | 3.083 | Not Started | Reevaluate justification |  |  | Lauren Chavez
Project Demo | 3.084 | Not Started | Obtain user requirements consensus |  |  | James DeCola
Project Demo | 3.085 | Completed | Obtain technical consensus |  |  | Jack Stromberg
Project Demo | 4 | Completed | Programming and Unit Testing (Phase 4) |  |  | Martie Feldtmann
Project Demo | 4.01 | In Progress | Decompose program modules |  |  | Martie Feldtmann
Project Demo | 4.011 | Completed | Identify program modules |  |  | James DeCola
Project Demo | 4.012 | Not Started | Identify program module input and output |  |  | Bridgette
Project Demo | 4.013 | Not Started | Identify reusable modules |  |  | James DeCola
Project Demo | 4.014 | Completed | Eliminate module redundancies |  |  | Bridgette
Project Demo | 4.02 | Completed | Develop program modules |  |  | Jack Stromberg
Project Demo | 4.021 | Deferred | Develop detailed module logic |  |  | Lauren Chavez
Project Demo | 4.022 | Completed | Validate module logic |  |  | Lauren Chavez
Project Demo | 4.023 | In Progress | Code module |  |  | Lauren Chavez
Project Demo | 4.024 | Deferred | Develop module test data |  |  | Lauren Chavez
Project Demo | 4.025 | Completed | Develop call and called stubs |  |  | Jack Stromberg
Project Demo | 4.026 | Deferred | Unit test program |  |  | Martie Feldtmann
Project Demo | 4.03 | Not Started | Update test/conversion procedures |  |  | Bridgette
Project Demo | 4.031 | Completed | Review test/conversion plans |  |  | Lauren Chavez
Project Demo | 4.032 | In Progress | Update test/conversion plans |  |  | Lauren Chavez
Project Demo | 4.04 | Completed | Management review / Phase 3 funding |  |  | James DeCola
Project Demo | 4.041 | Deferred | Plan next phase |  |  | Lauren Chavez
Project Demo | 4.042 | Not Started | Reevaluate development costs |  |  | Jack Stromberg
Project Demo | 4.043 | Deferred | Reevaluate justification |  |  | Jack Stromberg
Project Demo | 4.044 | Deferred | Obtain user requirements consensus |  |  | Lauren Chavez
Project Demo | 4.045 | Not Started | Obtain technical consensus |  |  | Lauren Chavez
Project Demo | 5 | Deferred | System Testing (Phase 5) |  |  | Martie Feldtmann
Project Demo | 5.01 | In Progress | Finalize integrated system test plan |  |  | James DeCola
Project Demo | 5.011 | In Progress | Review interim test procedures |  |  | James DeCola
Project Demo | 5.012 | Completed | Develop integration test procedures |  |  | Martie Feldtmann
Project Demo | 5.013 | In Progress | Develop integration test plan |  |  | Martie Feldtmann
Project Demo | 5.014 | Deferred | Assign integration test responsibilities |  |  | James DeCola
Project Demo | 5.015 | Deferred | Develop integration test data |  |  | James DeCola
Project Demo | 5.016 | Completed | Train data processing personnel |  |  | Bridgette
Project Demo | 5.02 | Not Started | Finalize user acceptance/training test plan |  |  | Martie Feldtmann
Project Demo | 5.021 | Deferred | Review interim test procedures |  |  | Lauren Chavez
Project Demo | 5.022 | Not Started | Develop user acceptance criteria |  |  | Jack Stromberg
Project Demo | 5.023 | Deferred | Develop final user acceptance test procedures |  |  | Martie Feldtmann
Project Demo | 5.024 | In Progress | Develop user acceptance test plan |  |  | Jack Stromberg
Project Demo | 5.025 | Deferred | Assign user acceptance test responsibilities |  |  | Bridgette
Project Demo | 5.026 | Completed | Develop user acceptance test data |  |  | Martie Feldtmann
Project Demo | 5.027 | Completed | Train users |  |  | Lauren Chavez
Project Demo | 5.03 | Deferred | Conduct integration test |  |  | Lauren Chavez
Project Demo | 5.031 | In Progress | Link programs and copy to test libraries |  |  | James DeCola
Project Demo | 5.032 | Deferred | Establish test files |  |  | James DeCola
Project Demo | 5.033 | Completed | Execute integration test |  |  | James DeCola
Project Demo | 5.04 | Completed | Conduct user acceptance/training test |  |  | Martie Feldtmann
Project Demo | 5.041 | In Progress | Establish user acceptance test files |  |  | James DeCola
Project Demo | 5.042 | Completed | Establish test files |  |  | Jack Stromberg
Project Demo | 5.043 | Completed | Execute user acceptance test |  |  | Bridgette
Project Demo | 5.05 | In Progress | Management review / Phase 3 funding |  |  | Jack Stromberg
Project Demo | 5.051 | In Progress | Plan next phase |  |  | Martie Feldtmann
Project Demo | 5.052 | Not Started | Reevaluate development costs |  |  | Lauren Chavez
Project Demo | 5.053 | Completed | Reevaluate justification |  |  | James DeCola
Project Demo | 5.054 | In Progress | Obtain user requirements consensus |  |  | James DeCola
Project Demo | 5.055 | Completed | Obtain technical consensus |  |  | Martie Feldtmann
Project Demo | 6 | In Progress | Installation (Phase 6) |  |  | Lauren Chavez
Project Demo | 6.01 | Completed | Finalize conversion plan |  |  | Martie Feldtmann
Project Demo | 6.011 | Not Started | Review interim conversion procedures |  |  | Jack Stromberg
Project Demo | 6.012 | Deferred | Develop conversion procedures |  |  | Bridgette
Project Demo | 6.013 | Completed | Develop conversion plan |  |  | Jack Stromberg
Project Demo | 6.014 | Completed | Assign conversion responsibilities |  |  | Lauren Chavez
Project Demo | 6.02 | Deferred | Convert files/database |  |  | Martie Feldtmann
Project Demo | 6.03 | Completed | Install software |  |  | Bridgette
Project Demo | 6.04 | Completed | Run systems in parallel |  |  | Bridgette
Project Demo | 6.05 | In Progress | Turn off old system |  |  | James DeCola
Project Demo | 6.06 | Completed | Management review |  |  | Martie Feldtmann
Project Demo | 6.061 | Completed | Obtain user requirements consensus |  |  | Bridgette
Project Demo | 6.062 | Completed | Obtain technical consensus |  |  | James DeCola
Project Demo | 6.063 | Deferred | Document recommended changes to architecture |  |  | Martie Feldtmann
Project Demo | 6.064 | In Progress | Document recommended enhancements to system |  |  | Bridgette

## Sheet2
No | Status
1 | Bridgette
2 | James DeCola
3 | Jack Stromberg
4 | Lauren Chavez
5 | Martie Feldtmann